PROJECT CLOSURE REPORT

Odoo ERP Integration

Jan-April 2025

1. Project Summary

| Item | Description |
| --- | --- |
| Project Name | Odoo ERP Implementation |
| Sponsor | Director of IT & Digital Transformation |
| Start Date | [Start Date] |
| End Date | [End Date] |
| Budget | KES [amount] |
| Scope | Implement Finance, Procurement, HR, CRM, and Inventory modules |
| Status | Completed (Go-live achieved + post-go-live support ended) |

2. Objectives & Outcomes

| Objective | Planned Outcome | Actual Outcome | Status |
| --- | --- | --- | --- |
| Automate manual processes | Full digitization of finance/procurement workflows | Achieved | ✅ |
| Improve reporting and decision-making | Real-time dashboards and custom reports | Achieved | ✅ |
| Enhance user collaboration | Integrated modules and employee portal | Partially Achieved (CRM pending integration) | ⚠️ |

3. Deliverables Completed

- Business Case

- Project Charter

- Communication & Change Management Plans

- Custom Odoo Modules

- Training & Adoption Program

- UAT Sign-Off & Quality Validation

- Go-Live Deployment

- Lessons Learned & Handover

4. Budget Summary

| Item | Budgeted | Actual | Variance |
| --- | --- | --- | --- |
| Software & Licenses | 4M | 4M | 0 |
| Implementation Services | 6M | 6.5M | +0.5M |
| Training | 1M | 0.9M | -0.1M |
| Contingency | 1M | 0.6M | -0.4M |
| Total | 12M | 12M | ✅ On Budget |

5. Project Performance (KPIs)

| KPI | Target | Actual |
| --- | --- | --- |
| UAT Pass Rate | ≥95% | 96.5% |
| Training Completion Rate | ≥90% | 97% |
| Post-Go-Live Incidents | ≤10 | 6 |
| User Satisfaction Score | ≥85% | 89% |

6. Risks & Issues

| Item | Mitigation | Outcome |
| --- | --- | --- |
| User resistance to new workflows | Change champions & phased training | Resistance decreased 75% |
| Data migration errors | Multiple validation cycles | Clean transfer achieved |
| Integration delays | Escalation to vendor | CRM integration deferred |

7. Lessons Learned

- Early user involvement in design reduces resistance.

- Sandbox environments are crucial for real training.

- Weekly stakeholder check-ins improved visibility.

- Vendor response time impacted timeline—build buffer in contracts.

8. Handover & Support

- Admin documentation delivered to internal IT.

- Knowledge transfer sessions held with in-house team.

- Odoo support contract signed for 6 months.

- Transitioned to internal Helpdesk support.

9. Sign-Off

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| [Sponsor Name] | Executive Sponsor | __________ | _______ |
| [Your Name] | Project Manager | __________ | _______ |
| [Dept. Leads] | Stakeholders | __________ | _______ |